## concrete test analysis
Date | Location | Concrete Grade | Slump (mm) | 7-Day Strength (MPa) | 28-Day Strength (MPa) | Required Strength (MPa) | Difference | Status | Parameter | Value
2025-01-01 | Block B | M20 | 114.3 | 14.33 | 22.43 | 20 | 2.43 | Pass | Total tests | 30
2025-01-04 | Block A | M25 | 95.1 | 16.29 | 26.06 | 25 | 1.06 | Pass | Failed | 12
2025-01-07 | Column Zone 1 | M20 | 113.5 | 14.63 | 20.04 | 20 | 0.04 | Pass | Passed | 18
2025-01-10 | Foundation | M30 | 79.5 | 21.47 | 30.5 | 30 | 0.5 | Pass | Failure % | 40%
2025-01-13 | Block A | M20 | 94.4 | 11.68 | 17.98 | 20 | -2.02 | Fail
2025-01-16 | Foundation | M30 | 105.8 | 22.25 | 30.11 | 30 | 0.11 | Pass
2025-01-19 | Block B | M30 | 116.4 | 19.09 | 33.39 | 30 | 3.39 | Pass
2025-01-22 | Block B | M30 | 114.5 | 18.06 | 30.63 | 30 | 0.63 | Pass
2025-01-25 | Block A | M30 | 110.5 | 21.49 | 33.61 | 30 | 3.61 | Pass
2025-01-28 | Block A | M25 | 112.9 | 16.26 | 26.67 | 25 | 1.67 | Pass
2025-01-31 | Column Zone 1 | M30 | 104.5 | 19.04 | 28.43 | 30 | -1.57 | Fail
2025-02-03 | Block B | M30 | 93.5 | 19.28 | 28.39 | 30 | -1.61 | Fail
2025-02-06 | Block A | M25 | 102.5 | 15.78 | 23.69 | 25 | -1.31 | Fail
2025-02-09 | Block B | M20 | 93.4 | 11.7 | 18.3 | 20 | -1.7 | Fail
2025-02-12 | Foundation | M20 | 92.4 | 14.23 | 21.51 | 20 | 1.51 | Pass
2025-02-15 | Block A | M25 | 119.9 | 18.54 | 27.37 | 25 | 2.37 | Pass
2025-02-18 | Block A | M20 | 94.9 | 13.5 | 18.43 | 20 | -1.57 | Fail
2025-02-21 | Foundation | M25 | 88.7 | 14.32 | 26.5 | 25 | 1.5 | Pass
2025-02-24 | Block A | M25 | 78.8 | 18.21 | 28.14 | 25 | 3.14 | Pass
2025-02-27 | Column Zone 2 | M20 | 83.9 | 14.23 | 22.63 | 20 | 2.63 | Pass
2025-03-02 | Block B | M20 | 93.7 | 11.09 | 21.46 | 20 | 1.46 | Pass
2025-03-05 | Block B | M20 | 83.9 | 14.98 | 17.29 | 20 | -2.71 | Fail
2025-03-08 | Foundation | M20 | 83.2 | 14.57 | 22.69 | 20 | 2.69 | Pass
2025-03-11 | Block A | M25 | 75.8 | 16.69 | 24.06 | 25 | -0.94 | Fail
2025-03-14 | Column Zone 1 | M30 | 105.2 | 22.42 | 28.93 | 30 | -1.07 | Fail
2025-03-17 | Foundation | M25 | 106.7 | 17.09 | 26.75 | 25 | 1.75 | Pass
2025-03-20 | Block B | M25 | 86.3 | 14.05 | 26.44 | 25 | 1.44 | Pass
2025-03-23 | Column Zone 1 | M20 | 91.5 | 11.12 | 18.85 | 20 | -1.15 | Fail
2025-03-26 | Block A | M20 | 106.5 | 14.2 | 19.95 | 20 | -0.05 | Fail
2025-03-29 | Block A | M30 | 88 | 19.74 | 28.96 | 30 | -1.04 | Fail

## Material approval status
Material Name | Supplier | Test Certificate Available | Approval Status | Parameter | Value
Admixture | BuildWell Ltd | No | Pending | Total Materials | 20
TMT Steel Fe500 | ABC Suppliers | Yes | Approved | Total Approved | 13
River Sand | InfraSource | Yes | Approved | Total Pending | 7
Coarse Aggregate | Structura Pvt Ltd | No | Pending | Pending % | 35%
TMT Steel Fe500 | BuildWell Ltd | No | Pending | Approved % | 65%
Coarse Aggregate | ABC Suppliers | Yes | Approved
Cement OPC 53 | BuildWell Ltd | Yes | Approved
TMT Steel Fe500 | InfraSource | Yes | Approved
Admixture | Structura Pvt Ltd | No | Pending
Coarse Aggregate | ConcreteMart | No | Pending
River Sand | Structura Pvt Ltd | Yes | Approved
TMT Steel Fe500 | InfraSource | No | Pending
Admixture | InfraSource | No | Pending
Admixture | Structura Pvt Ltd | Yes | Approved
TMT Steel Fe500 | ConcreteMart | Yes | Approved
River Sand | ABC Suppliers | Yes | Approved
Cement OPC 53 | Structura Pvt Ltd | Yes | Approved
Coarse Aggregate | ConcreteMart | Yes | Approved
Admixture | InfraSource | Yes | Approved
River Sand | BuildWell Ltd | Yes | Approved

## Site inspection log
Date | Activity | Inspector Name | Observation | Non-Conformance | Remarks | Parameter | Value
2025-02-01 | Formwork | Engineer Ravi | Minor deviation observed | Yes | Rectification required | Total inspections | 40
2025-02-02 | Formwork | Engineer Priya | Minor deviation observed | Yes | Rectification required | Non-conformance | 21
2025-02-03 | Concrete Pouring | Engineer Ravi | Minor deviation observed | Yes | Rectification required | NC rate % | 52.5%
2025-02-04 | Foundation Excavation | Engineer Priya | Minor deviation observed | Yes | Rectification required
2025-02-05 | Concrete Pouring | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-02-06 | Rebar Fixing | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-02-07 | Foundation Excavation | Engineer Meera | Minor deviation observed | Yes | Rectification required
2025-02-08 | Rebar Fixing | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-02-09 | Concrete Pouring | Engineer Meera | Work as per drawing | No | Approved
2025-02-10 | Rebar Fixing | Engineer Priya | Minor deviation observed | Yes | Rectification required
2025-02-11 | Curing | Engineer Arjun | Work as per drawing | No | Approved
2025-02-12 | Formwork | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-02-13 | Formwork | Engineer Priya | Work as per drawing | No | Approved
2025-02-14 | Curing | Engineer Priya | Minor deviation observed | Yes | Rectification required
2025-02-15 | Rebar Fixing | Engineer Priya | Work as per drawing | No | Approved
2025-02-16 | Concrete Pouring | Engineer Ravi | Work as per drawing | No | Approved
2025-02-17 | Formwork | Engineer Meera | Work as per drawing | No | Approved
2025-02-18 | Curing | Engineer Priya | Work as per drawing | No | Approved
2025-02-19 | Foundation Excavation | Engineer Meera | Work as per drawing | No | Approved
2025-02-20 | Concrete Pouring | Engineer Ravi | Minor deviation observed | Yes | Rectification required
2025-02-21 | Formwork | Engineer Meera | Minor deviation observed | Yes | Rectification required
2025-02-22 | Rebar Fixing | Engineer Ravi | Work as per drawing | No | Approved
2025-02-23 | Rebar Fixing | Engineer Ravi | Minor deviation observed | Yes | Rectification required
2025-02-24 | Concrete Pouring | Engineer Ravi | Work as per drawing | No | Approved
2025-02-25 | Formwork | Engineer Priya | Work as per drawing | No | Approved
2025-02-26 | Curing | Engineer Priya | Work as per drawing | No | Approved
2025-02-27 | Foundation Excavation | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-02-28 | Concrete Pouring | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-03-01 | Curing | Engineer Priya | Work as per drawing | No | Approved
2025-03-02 | Rebar Fixing | Engineer Ravi | Minor deviation observed | Yes | Rectification required
2025-03-03 | Curing | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-03-04 | Formwork | Engineer Arjun | Minor deviation observed | Yes | Rectification required
2025-03-05 | Formwork | Engineer Priya | Minor deviation observed | Yes | Rectification required
2025-03-06 | Formwork | Engineer Ravi | Work as per drawing | No | Approved
2025-03-07 | Concrete Pouring | Engineer Priya | Work as per drawing | No | Approved
2025-03-08 | Concrete Pouring | Engineer Ravi | Work as per drawing | No | Approved
2025-03-09 | Curing | Engineer Priya | Work as per drawing | No | Approved
2025-03-10 | Formwork | Engineer Priya | Minor deviation observed | Yes | Rectification required
2025-03-11 | Curing | Engineer Ravi | Work as per drawing | No | Approved
2025-03-12 | Formwork | Engineer Priya | Work as per drawing | No | Approved